# How To Hold A Run/Race

Below are instructions for planning and holding a Run/Race..  This event could be as large as you want to make it.

## FIRST STEPS

- Put together a planning committee and determine who will hold each position.  One person could hold multiple positions.  See job descriptions on pages 2 & 3.

  - Run/Race Director

  - Publicity/Public Relations Coordinator

  - Sponsorship Coordinator

  - Web Designer

  - Volunteer Coordinator

  - Finance Coordinator

  - Registration Coordinator

  - Graphic Artist

  - Run/Walk Finish Line Coordinator

- Schedule and hold regular meetings with your planning committee.

- Decide on Run/Race Details.

  - Date

  - Location (starting and ending the race/run in the same place is best)

    - You will need to have bathrooms on site – can rent porta-potties if needed

  - Length of Route

  - Start Time(s)

  - Anticipated number of runners

  - Address for runners to mail in registration forms

  - Choose Run/Race route

    - www.mapmyrun.com is helpful. There is a small fee to join

    - Consider that you may need insurance to cover your run/race.  Look into city vs. campus

    - Consider that you will need to obtain permission for using campus or city property and there may e an application process with deadlines for turning in the paperwork.

    - Try to minimize crossing streets – use bike paths, etc.

- Decide on how you will pay for your run/race.

  - Obtain sponsors to pay for race expenses or to donate needed items.

  - Or…Take the costs of the run/race out of the money raised.

- Set a budget and determine how much money you need to raise from sponsors.

- Determine how you will do your banking.

  - Determine who the sponsors will write the checks to.

  - Determine who the runners/walkers will write checks to when registering.

- Determine whether runners/walkers will donate a suggested amount or if they will each raise pledges.  More money will be raised with pledges.  You could give the runners/walkers a choice.

- Put together a Run/Race Entry Form and Pledge Form.  See sample below on pages 4 & 5.

### ADDITIONAL TASKS TO COMPLETE

- Choose awards and order them.

- Order T-Shirts.  Be sure to order extra shirts for race-day registrations.

- Order race numbers.  The following website has them: www.rainbowracing.com .  Your can order the generic pull tag type “C”

- Get pins for race numbers and envelopes or bags for race packets.

- Determine race day schedule and map out layout of race day activities.

- Determine what will go into race packets.

- Arrange for a time to stuff race packets.

### COMMITTEE MEMBER JOB DESCRIPTIONS

## Publicity/Public Relations Coordinator

- Type up a press release

- Posters/flyers/race forms

  - Have graphics person design posters and flyers, and type up a blurb for church bulletins.

  - Determine where they will be distributed to (get permission from some businesses to distribute registration forms).

  - Assign locations to volunteers to distribute posters, flyers, registration forms, and church bulletin blurbs.

- Send press releases to area newspapers, television and radio stations, post on community calendars.

- Follow up with TV and radio stations to get TV/radio interviews.

- Arrange to have race times posted in newspaper after the race.

## Sponsorship Coordinator

- Type up sheet with sponsorship levels (include donation amounts required for each level, as well as listing the benefits received at each level).

- Identify and solicit businesses for $ sponsorship (avoid conflicts of interest between sponsors such as not asking businesses that are competitors)- bring along copies of the sheet with sponsorship levels.

- Identify gift in-kind needs and solicit.

  - Post-race refreshments such as bagels, carbs, bottled water, hot chocolate.

  - Porta-potties if needed.

  - Borrow a sound system (you will need this at start/finish and for awards ceremony).

  - Tables and chairs for water stations, registration, volunteer check-in, packet pick-up, and post-race refreshments.

  - Water dispensers and cups for water stations and post-race drinks.

  - Tents in case it rains.

  - Walkie-talkies to communicate on race day (or use cell phones).

  - Race clock, cones, vests for road marshals, starting gun, finish line chutes.

  - T-shirt discount at screen printing business.

- Ensure that the sponsors receive what was promised.

- Arrange for all donations to be picked up/ delivered for race day.

- Write thank you notes to sponsors, send tax deductible receipts if applicable.

## Web Designer

- See www.cvjusticerun.org for ideas.

- Choose website domain name.

- Post pictures and race times after the race.

- Consider online registration and incorporate into website.

## Volunteer Coordinator

- Determine # of volunteers needed.

- Recruit volunteers.

- Pre-print instructions and maps for volunteers.

- Communicate with volunteers regarding instructions, etc.

- Volunteer waiver.

- Coordinate volunteer check-in on race day.

## Finance Coordinator

- Collect registration and sponsorship money.

- If you are doing tax deductions, determine the value of goods received by runners and subtract that from their donation as per IRS guidelines.

- Write checks for expenses, reimbursements to committee members.

## Registration Coordinator

- Collect registration forms.

- Put runner information in database.

- Determine how to transfer runner information onto race numbers and packets (name, gender, age category, and hometown/state).

- Coordinate packet-pickup and registration on run/race day.

## Graphic Designer

- Design posters, flyers, blurbs for church bulletins.

- Design T-Shirts.

## Run/Walk Route/Finish Line Coordinator

- Help plan the route.

- Determine where road marshals should be placed, where to put cones and signs on the route.

- Learn how to use the time clock, starting gun, stopwatch, etc.

- Be in charge of finish line volunteers on race day (collect tags from runners, post times, etc.).

- Type up race results to post on website and possibly have printed in newspaper.

Youth Group Mission Trip Fund-Raiser Run/Walk Entry Form

# Entry/Registration Form

The entry fee is $25 per adult, $15 per student under 18 years of age (non-tax deductible as allowed by law) which includes an event day T-shirt.

Please fill out form and submit on event day. To ensure the availability of the T-shirt on event day, please email the information in the shaded area to yourname@aol.com or call 678-555-5555 no later than September 22, 2010.

Name: _______________________________________________________

Address: _____________________________________________________

City/State/Zip: _________________________________________________

Phone: _____________________________

Email: ______________________________

T-shirt Size(please check one):

Youth: XS(2/4) ____ S(6/8) ____ M(10-12) ____ L(14-16) ____

Adult Small ____ M ____ L ____ XL ____ XXL ____ XXXL ____

Statement of Consent: I understand the risks involved in participating in this Run/Walk and willingly and voluntarily accept these risks. I attest that I’m physically fit for this event. I grant permission to XYZ Church to use photos/images/and/or quotations from me in accounts and promotions of this event.

Signature/Date: ________________________________________________

Parent or Guardian signature if under 18 years of age.

Signature/Date: _______________________________________________

$25 Entry Fee Paid ____

$15 Entry Fee Paid ____

Youth Group Mission Trip Fund-Raiser Run/Walk Entry Form

Pledge Form

Instructions:

1. Sign up supporters and list the amount of their pledge on this form. Collect all donations prior to the Youth Group Mission Trip Fund-Raiser Run/Walk on October 2, 2010.

Make checks payable to: XYZ Church Youth Group.

2. Submit all your donations in an envelope at the start of the Run/Walk or give them to Jean Johnson.  You can mail them to:  XYZ Church, 123 First Street, Your City, State Zip.

3 All pledges must be turned in on October 2nd to qualify for the “Most Pledges Collected Prize.

| Donor Name | Donor Address | Pledge Amount | Receipt Requested? |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |
| 6. |  |  |  |
| 7. |  |  |  |
| 8. |  |  |  |
| 9. |  |  |  |
| 10. |  |  |  |
| 11. |  |  |  |
| 12. |  |  |  |
| 13. |  |  |  |
| 14. |  |  |  |
| 15. |  |  |  |
| 16. |  |  |  |
| 17. |  |  |  |
| 18. |  |  |  |
| 19. |  |  |  |
| 20. |  |  |  |

## TOTAL PLEDGED: ________________

Youth Group Mission Trip Fund-Raiser Run/Walk is a fund-raising event. All proceeds from this event will be donated to XYZ Church which is a 501(c)3 non-profit organization. All donations are tax deductible and will be used to fund the youth group’s mission trip to Any City, USA.